|  |  |  | # MyPanic ## January 2026 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | # Product Definition Outline & Product Plan |  |  |  |  |
|  | # MyPanic Safety System ## Product Definition, Development Strategy, Manufacturing Plan, and Implementation Roadmap Version 1 Project Specification Document Date: January 2026 Prepared For: MyPanic Team 1. EXECUTIVE SUMMARY MyPanic is a hybrid safety ecosystem consisting of: - A mobile app, providing proactive, context-aware personal safety features, intelligent ride monitoring, community safety intelligence, and automated escalation logic. - A wearable panic trigger (MyPanic Clip Alarm), a Bluetooth-enabled physical trigger that instantly activates the app’s safety protocols, designed for rapid, discrete activation. Together, these products function as a connected, preventive, and responsive safety solution tailored for women’s everyday contexts (rides, meet-ups, transit, public spaces) and extend beyond reactive SOS apps by adding context awareness, predictive risk indicators, and community intelligence. Primary objectives: - Deliver a fully functioning MVP within a 6-month cycle. - Establish local manufacturing and supply partnerships. - Validate solution with pilots on university campuses and community organisations. - Prepare for volume production by 12-15 months. - PRODUCT FEATURES (DETAILED) 2.1 MyPanic App - Functional Specifications Core MVP functionalities (Version 1): - Instant SOS Activation - Via app button and via Bluetooth Clip Alarm trigger. - Sends live GPS location to trusted contacts. - Trusted Contacts Module - Add/edit emergency contacts. - Customisable alert methods (SMS fallback, push). - Live Tracking Session - Real-time location sharing link for responders. - Ride Track - Users share ride service trip link. - Monitors route deviations, long stops, and unusual movement indicators. - Flags WHEN matched against community-reported drivers or risk patterns. - Safety Trails - Users can pre-register meet-ups with expected check-ins. - Auto escalation on missed confirmations. - AI-powered Movement and routine analysis - Incident Vault - Secure storage of profile links, screenshots, notes, and session metadata. - Automatic Escalation Logic - Sensor fusion (GPS, accelerometer, BLE disconnect) triggers if user unresponsive. Innovative context-aware features (Version 1/1.1): - Auto Snatch Detection - Uses motion and Bluetooth state to infer forced phone removal. - Nearby Sister Awareness - Silent proximity notifications to other opted-in MyPanic users within a set radius. - No identity revealed unless consented. Planned (post-MVP) features: - Driver/ride risk scoring based on aggregated flags. - Integration with SafePoint Network (partner safe locations). - Pattern analysis and risk heatmaps. 2.2 MyPanic Clip Alarm - Functional Specifications Primary purpose: A discreet, wearable panic trigger that sounds a loud siren alarm and instantly activates the core safety workflow in the app, even when the phone is locked or in a pocket. Key functions: - Bluetooth connection to paired smartphone (BLE) - Single/double press logic to trigger SOS - Haptic feedback on activation - Low-power design for extended battery life - QR printed on device linking to the user’s emergency profile (viewable on web when scanned) Form factor targets: - Clip-on design (bag/clothing) - Lightweight (<30g) - Simple LED/haptic indication 3. DEVELOPMENT ROADMAP & MILESTONES This timeline is based on a dedicated small team (project manager, firmware engineer, app devs, designer) and local manufacturing partnerships for early prototyping. Phase; Duration; Key Activities; Deliverables. Phase A - Planning & Specification; 2 weeks; Detailed requirements, hardware spec, software spec, risk analysis; Functional spec documents. Phase B - Hardware Design & Prototyping; 6 weeks; Select BLE module, design PCB, battery/switch/housing design; Prototype PCBs, initial firmware. Phase C - App MVP Development; 8 weeks (parallel); Build core app features, API, ride track logic; Beta app build (Android first, then iOS). Phase D - Hardware Integration & Firmware; 6 weeks; BLE pairing, SOS triggers, sensor integration; Firmware v0.9. Phase E - Local Fabrication & Assembly; 4 weeks; Prototype assembly via local EMS partners; 5-10 prototype units. Phase F - Testing & Validation; 6 weeks; Functional, stress, usability, field testing; Test reports, UX feedback. Phase G - Iteration & Quality Improvements; 4 weeks; Bug fixes, hardware adjustments; Release candidate MVP. Phase H - Pilot Deployment; 8 weeks; Campus/NGO pilot, monitoring; Pilot performance report. Total Duration: 6 months from start to pilot launch. 4. DEVICE COMPONENTS & PROCUREMENT 4.1 Critical Hardware Components Component; Purpose. BLE SoC (Bluetooth Low Energy module); Wireless link to phone. Microcontroller unit; Handles input & BLE communication. Rechargeable battery; Power source. Button + switch; User trigger. Haptic motor; Feedback. LED indicator; Status. Passive parts (resistors, caps); Standard electronics. PCB board; Mounting and connections. Enclosure; Housing. Estimated approximate costs per unit (prototype quantities): - BLE SoC: R35–R80 - MCU tier: R25–R60 - Battery + charge circuit: R30–R80 - Button & haptics: R15–R30 - PCB & assembly: R40–R120 - Enclosure (3D print prototype) R20–R60 Local procurement available from electronics stores like Leobot Electronics and Hobbytronics. (Leobot Electronics) 4.2 South African Component & PCB Sourcing Local suppliers include: - Deman Manufacturing - electronic components, SMT assembly, PCB procurement and supply. (deman-mfg.co.za) - Leobot Electronics - microcontrollers, modules, sensors. (Leobot Electronics) - Hobbytronics - basic electronic components and prototyping parts. (hobbytronics.co.za) - Rabtron - components, tools, microcontrollers. (rabtron.co.za) For PCBs: - Repro Supplies - local PCB manufacture and assembly in Boksburg. (Repro Supplies) - Procircuit - PCB supply and assembly services in Cape Town. (Procircuit) EMS Partners for assembly/testing: - Microtronix Manufacturing (Johannesburg) - turnkey assembly and quality control. (Microtronix Manufacturing) - Jemstech (Centurion) - EMS for prototypes and low to medium volume. (jemstech.co.za) - Production Logix (Pinetown) - high-standard PCB assembly and turnkey services. (Production Logix - Your design, on track) These partners can provide: - PCB assembly - Surface mount technology (SMT) - Through-hole assembly - Proto and volume manufacturing 5. REQUIRED PARTIES & RESPONSIBILITIES 5.1 Internal Project Team - Product Manager: Oversees planning, milestones, budget management - Hardware Engineer: Designs hardware, selects components, liaises with EMS partner - Firmware Engineer: To Write embedded software for Clip Alarm - Mobile App Developers: Build app features (Android, iOS) - UX/UI Designer: App interface, interaction design - QA/Test Engineers: Verify hardware and software quality 5.2 External Partners - EMS / PCB Assembly Partner: Repro Supplies / Deman / Microtronix / Procircuit / Jemstech for manufacturing - Component Distributors: Deman / Leobot / Hobbytronics / Rabtron for parts - Enclosure Fabricator: Local 3D printing shops or injection mould tooling partners - Testing Labs (optional): For EMC/EMI testing if scaling beyond MVP 6. DESIGN & DEVELOPMENT FLOW - Product requirements - hardware spec - schematic design - PCB layout - fabrication - SMT assembly - prototype units - Firmware development - BLE + feature integration - App backend API + frontend builds - Hardware and app integration testing - Field testing with minor user group - Iteration - pilot production - pilot deployment 7. TESTING & QUALITY Levels of testing required: - Functional prototype test - BLE pairing reliability - Activation latency tests - Stress & environmental (drops, heat) - Battery test under real usage - App stability across devices - Usability testing with female participants Quality standards will be documented, and the production runs must include inspection reports (optical, functional). 8. PILOT DEPLOYMENT PLAN Target groups: - University campuses - Women’s organisations - Night-shift worker cohorts Pilot scope: - 50-100 Clip devices - App release to limited participants - User feedback collected through surveys - Usage data analytics Pilot duration: 8-12 weeks - SCALE & PRODUCTION After successful pilot: - Refine BOM for cost reduction - Move to injection moulded enclosure - Scale EMS partner production for units 500-5,000 - Bulk component procurement for lower per-unit cost 10. RISKS & MITIGATION Risk; Mitigation. BLE pairing instability; Firmware refinement & test devices. High local component cost; Blend local + international procurement. Manufacturing delays; Multiple EMS partners. Firmware bugs; Continuous integration + automated testing. Data privacy concerns; Secure design + compliance. 11. COMPLIANCE & CERTIFICATION (LATER PHASE) For scaling after MVP: - Product safety standards - FCC/CE for exporting - EMC/EMI compliance |  |